## Sheet1
status | who ? | kind | scope | task | notes
DONE | lexou | manage | meta | excel todo list
DONE? |  | design | meta | what's the story ?
DONE? |  | design | engine | figure out all captures we need
DONE? |  | design | stage | basic capture tutorial rooms
SKIP |  | design | stage | large-ish overworld
DONE | kitsu, lexou | design | stage | dark cave with candlebois
SKIP |  | design | stage | castle with statue puzzles
SKIP |  | design | stage | endgame puzzles using all captures
DONE | kitsu | design | enemy | endgame boss battle chase sequence
DONE | joey | music | engine | title screen
DONE | joey | music | engine | intro cutscene
DONE | lexou | music | stage | overworld
SKIP | joey | music | stage | cave dungeon
DONE | joey | music | stage | boss dungeon
DONE | joey | music | enemy | boss battle
DONE? | joey | music | engine | end credits
WIP | lexou | code | engine | HTML5 web build
DONE | kitsu | art | engine | pixel font | used an old font (it's allowed in the rules for fonts only)
TODO | kitsu | code | engine | galloway splash screen
DONE | adam | art | engine | galloway splash screen
SKIP |  | code | engine | ending credits
DONE | shaunak | code | engine | title screen
DONE | adam | art | engine | title screen
DONE | shaunak | code | engine | cutscene slideshow system
DONE | adam, pik | art | engine | game start cutscene
WIP | pik | art | engine | game ending cutscene
DONE | kitsu | code | engine | game over
SKIP | shaunak | code | engine | menu controls
SKIP | joey | sound | engine | menu accept
SKIP | joey | sound | engine | menu cancel
SKIP | shaunak | code | engine | pause menu
SKIP | joey | sound | engine | pause menu
SKIP |  | art | engine | pause menu
DONE | kitsu | code | engine | in-game HUD
DONE |  | art | engine | in-game HUD
DONE | kitsu | code | engine | controller support
DONE? | kitsu | code | engine | 2.5D layering
SKIP | kitsu | code | engine | 2.5D altitude & shadows
DONE | kitsu | code | engine | terrain collisions
DONE | kitsu | code | engine | entity collisions
DONE | kitsu | code | engine | room transitions
DONE | shaunak | code | engine | room transitions zelda scrolling
DONE | kitsu | code | engine | falling off the stage | should reset the room if this happens (to just respawn everything)
DONE | kitsu | code | engine | enemy capture mechanic
DONE | kitsu | code | effect | light/dark mechanic
DONE | kitsu | code | effect | explosion
DONE | joey | anim | effect | explosion
DONE | joey | sound | effect | explosion
DONE | kitsu | anim | effect | projectile mask
DONE | kitsu | anim | effect | capture enter
DONE | kitsu | anim | effect | capture exit
DONE | prism | art | player | idle
DONE | kitsu | code | player | movement
DONE | prism | anim | player | movement
DONE | kitsu | code | player | sword attack
DONE | joey, kitsu | sound | player | sword swing whiff
DONE | joey, kitsu | sound | player | sword swing hit
DONE | kitsu | code | player | projectile capture mask
DONE | joey | sound | player | projectile mask throw
DONE | joey, kitsu | sound | player | projectile mask capture
DONE | joey, kitsu | sound | player | enemy capture exit
DONE | kitsu | code | player | player damage
DONE | joey, kitsu | sound | player | player damage
DONE | kitsu | code | player | player death
DONE | joey, kitsu | sound | player | player death
DONE |  | anim | player | player death
DONE | kitsu | code | enemy | enemy damage
DONE | joey, kitsu | sound | enemy | enemy damage
DONE | kitsu | code | enemy | enemy death
DONE | joey, kitsu | sound | enemy | enemy death
DONE | kitsu | code | enemy | spider
DONE | kitsu | code | enemy | spider capture
DONE | knight | art | enemy | spider idle
SKIP |  | art | enemy | spider walk
DONE | kitsu | code | enemy | statue
DONE | kitsu | code | enemy | statue capture
DONE | knight | art | enemy | statue
DONE | joey, kitsu | sound | enemy | statue jump landing
DONE | kitsu | code | enemy | candle (light)
DONE | kitsu | code | enemy | candle capture
DONE | knight | art | enemy | candle idle
SKIP |  | anim | enemy | candle move
DONE | kitsu | code | enemy | flyer (ghost)
DONE | kitsu | code | enemy | flyer capture
DONE | lexou | art | enemy | flyer idle
DONE? | lexou | anim | enemy | flyer move
SKIP | kitsu | code | enemy | jumper (frog)
SKIP | kitsu | code | enemy | jumper capture
WIP | knight | art | enemy | jumper idle
SKIP |  | anim | enemy | jumper jump
SKIP | joey | sound | enemy | jumper jump
DONE | kitsu | code | enemy | roller (skeleton)
DONE | kitsu | code | enemy | roller capture
DONE | kitsu | art | enemy | roller idle
DONE | kitsu | anim | enemy | roller roll
SKIP | kitsu | code | enemy | exploder
SKIP | kitsu | code | enemy | exploder capture
SKIP |  | art | enemy | exploder idle
SKIP |  | anim | enemy | exploder move
DONE | kitsu | code | enemy | reaper boss
DONE | knight | art | enemy | reaper boss
SKIP |  | anim | enemy | reaper boss
SKIP | joey | sound | enemy | reaper boss
DONE | kitsu | code | stage | switch button (on floor)
DONE | joey | art | stage | switch button (on floor)
DONE | joey, kitsu | sound | stage | switch button (on floor)
DONE | kitsu | code | stage | switch lever (to hit)
DONE | joey | art | stage | switch lever (to hit)
DONE | joey, kitsu | sound | stage | switch lever (to hit)
DONE | kitsu | code | stage | switchable door
DONE | adam | art | stage | switchable door
DONE | joey, kitsu | sound | stage | switchable door
DONE | adam | art | stage | tiles: grass floor
DONE | adam | art | stage | tiles: grass cliff
DONE | adam | art | stage | tiles: rocky floor
DONE | adam | art | stage | tiles: rocky cliff
DONE | adam | art | stage | tiles: brick floor
DONE | adam | art | stage | tiles: brick wall
DONE | adam | art | stage | tiles: cave floor
DONE | adam | art | stage | tiles: cave walls
DONE | adam | art | stage | tiles: stairs
DONE | adam | art | stage | tiles: bridges
DONE | adam | art | stage | object: wide tree
DONE | adam | art | stage | object: thin tree
DONE | adam | art | stage | object: dead wide tree
DONE | adam | art | stage | object: dead thin tree
DONE | adam | art | stage | object: pine tree
DONE | adam | art | stage | object: rocks
DONE | adam | art | stage | object: pots
DONE | adam | art | stage | object: cave entrance
DONE | adam | art | stage | object: cave stalagmites
DONE | adam | art | stage | object: tombstone
DONE | adam | art | stage | object: door entrance